## Sheet1
Ascentis Global
Project One Pager
Prepared by: |  | Sawood |  |  | Date: | 2018-04-03
Project Name: |  | PakMaterial
Project Description B2C Construction Material Website
Project Start Date |  | 26/03/2018 |  | Tagetted Completion Date: |  |  | 04/05/2018 (30 Working days)
S.no | Milestones | Target Date | Status | Comments
1 | Template Embeded | 27/3/2018 | Completed
2 | Register Vendor with Email Verification | 28/3/2018 | Completed | Verification Done , need to check email on live server
3 | Facebook Login Testing | 29/3/2018 | Pending | Need hosting and ssl for facebook live testing
4 | Vendor Login Section | 30/3/2018 | Completed
5 | Admin Login / DashBoard | 2018-02-04 | Completed
6 | List of Vendor with status | 2018-03-04 | Completed | Approve or Reject Users
7 | Add / Edit / Main Category and Sub Categories | 2018-05-05 | Completed | For Admin
8 | Sent Verification Email | 2018-06-04 | Completed | Verification email is working . Testing remaining on pakmaterial domain because the domain is not working
9 | Create Vendor Profile | 2018-09-04 | Working | Add is done / edit is pending
10 | Vendor Profile Front View | 2018-09-04 | Working | For Vendor
11 | Buyer Login / DashBoard | 2018-10-04 | Pending | Simple buyer login (social media login will be integerated later)
12 | Add Vendor Profile Review/Rating | 2018-12-04 | Pending | Regereted Buyer will add review and rating
13 | Review and Rating Management by Admin | 13/4/2018 | Pending | Admin will approve and reject buyers review
14 | Buyer List of Review with Status | 13/4/2018 | Pending | Pending / Rejected / Approved
15 | Product Add / Edit | 2018-12-04 | Pending | Product Add / Edit
16 | Prodcut management by Admin | 13/4/2018 | Pending | Admin will approve and reject buyer product
17 | Product Front End View |  | Pending
18 | Product Compare |  | Pending
Red Flags
Outstanding matters to resolve
Hosting / SMS Service / Email Service
Financial matters |  | Rs. |  | Project Team
Total Project Price |  | 130000 |  | Name | Time spent todate |  | Comments
Billed amount |  | 0 |  | Moiz | Full Time
Received amount |  | 0 |  | Sawood | Full Time
Balance |  | 130000 |  | Talha | Full Time
Reasons for any delay